## Tabelle1
Sprint Review Protocol
Sprint No: |  | 2
Date & Time |  | 2024-04-16
Group Number |  | 5
Participant 1 |  | Elaine Fink
Participant 2 |  | Sonja Lechner
Participant 3 |  | Kevin Alexander
Participant 4 |  | Niklas Brandtner
Participant 5 |  | Luis Böhler
Mentor |  | Lena Oswald
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
7 | Items per Drag & Drop im Grid plazieren können | 10 |  | -10
8 | Session für User | 5 |  | -5 |  |  | Pair programming
9 | Profil ( User Daten ) | 15 |  | -15 |  |  | Pair programming
10 | Register & Login | 5 |  | -5 |  |  | Pair programming
11 | Datenbank anlegen | 10 |  | -10 |  |  | Pair programming
20 | Register und Login mit Datenbank verbinden | 10 |  | -10 |  |  | Pair programming
6 |  |  |  | -55 | 0 | 0
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol