## Tabelle1
Sprint Review Protocol
Sprint No: |  | 6
Date & Time |  | 2024-06-11
Group Number |  | 5
Participant 1 |  | Elaine Fink
Participant 2 |  | Sonja Lechner
Participant 3 |  | Kevin Alexander
Participant 4 |  | Niklas Brandtner
Participant 5 |  | Luis Böhler
Mentor |  | Lena Oswald
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
29 | Grid stylen | 10 | 3 | -7 | 1
28 | Charcterlist stylen | 10 | 10 | 0 | 1
12 | Charakter/Backpacks bearbeiten | 10 | 10 | 0 | 1
7 | Items per Drag & Drop im Grid plazieren können | 10 | 7 | -3 |  | 1
25 | Speichern der Itempositionen in der DB | 15 | 9 | -6 |  | 1
14 | Items in unterschiedlichen Größen | 15 | 16 | 1 | 1
31 | Itemlist stylen | 10 | 0 | -10 |  | 1
7 |  |  |  | -25 | 4 | 3
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol