## Tabelle1
Sprint Review Protocol
Sprint No: |  | 5
Date & Time |  | 2024-05-28
Group Number |  | 5
Participant 1 |  | Elaine Fink
Participant 2 |  | Sonja Lechner
Participant 3 |  | Kevin Alexander
Participant 4 |  | Niklas Brandtner
Participant 5 |  | Luis Böhler
Mentor |  | Lena Oswald
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
13 | Gridgröße nach Strength Modifier anpassen | 5 | 6 | 1 | 1
16 | Schriftarten stylen | 10 | 8 | -2 | 1
27 | Forms stylen | 10 | 10 | 0 | 1
28 | Lists/ Sidebars stylen | 10 | 0 | -10 |  | 1
29 | Grid stylen | 10 | 11 | 1 | 1
30 | Buttons stylen | 5 | 4 | -1 | 1
6 |  |  |  | -11 | 5 | 1
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol