## Tabelle1
Sprint Review Protocol
Sprint No: |  | 1
Date & Time |  | 2024-04-02
Group Number |  | 5
Participant 1 |  | Elaine Fink
Participant 2 |  | Sonja Lechner
Participant 3 |  | Kevin Alexander
Participant 4 |  | Niklas Brandtner
Participant 5 |  | Luis Böhler
Mentor |  | Lena Oswald
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
2 | Grid Layour erstellen | 10 | 10 | 0 | 1
3 | Itemliste rechts im Layout hinzufügen | 2 | 2 | 0 | 1 |  | Pair programming
4 | Ordnerstruktur anlegen | 1 | 1 | 0 | 1
5 | Item Icons erstellen | 5 | 4 | -1 | 1 |  | Pair programming
6 | Mock Ups für die einzelnen Seite erstellen | 8 | 7 | -1 | 1 |  | Pair programming
5 |  |  |  | -2 | 5 | 0
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol