## Tabelle1
Sprint Review Protocol
Sprint No: |  | 6
Date & Time |  | 2024-07-01
Group Number |  | 5
Participant 1 |  | Elaine Fink
Participant 2 |  | Sonja Lechner
Participant 3 |  | Kevin Alexander
Participant 4 |  | Niklas Brandtner
Participant 5 |  | Luis Böhler
Mentor |  | Lena Oswald
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
7 | Items per Drag & Drop im Grid plazieren können | 10 | 10 | 0 | 1
32 | Video erstellen | 3 | 3 | 0 | 1
34 | Deployment Mnual erstellen | 2 | 2 | 0 | 1
33 | User Manual erstellen | 3 | 3 | 0 | 1
25 | Speichern der Itempositionen in der DB | 15 | 14 | -1 | 1 |  | Pair Programming
31 | Itemlist stylen | 10 | 8 | -2 | 1
6 |  |  |  | -3 | 6 | 0
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol