## Tabelle1
Sprint Review Protocol
Sprint No: |  | 3
Date & Time |  | 2024-04-30
Group Number |  | 5
Participant 1 |  | Elaine Fink
Participant 2 |  | Sonja Lechner
Participant 3 |  | Kevin Alexander
Participant 4 |  | Niklas Brandtner
Participant 5 |  | Luis Böhler
Mentor |  | Lena Oswald
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
24 | Landing Page | 10 | 9 | -1 | 1
21 | Change Password bei Profil hinzufügen | 8 | 5 | -3 | 1
26 | Profil bearbeiten | 8 | 5 | -3 | 1
22 | Charakter/Backpacks erstellen | 10 |  | -10
19 | Charakter Übersicht pro User | 15 |  | -15
12 | Charakter/Backpacks bearbeiten | 10 |  | -10
23 | Charakter/Backpacks löschen | 5 |  | -5
7 |  |  |  | -47 | 3 | 0
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol